## Faculty Growth
Faculty Growth: PLU SoN Will have a stable (right structure and faculty mix), engaged (sense of community), developed (function, understanding, preparation) faculty. https://docs.google.com/document/d/1YKStcr3oXQL7Qd_-4vMH-gXP-rxPMq5mz3VQP_sKCSU/edit
Goal | Strategy | Action | Dates | Person(s) Responsible
Stability: The school of Nursing will recruit and retain highly qualified faculty. 3-5 year goal: Cultivate a robust and highly qualified faculty through targeted recruitment and promoting a culture that facilitates retention. | 1.A. Increase full time faculty (Staffing number): goal of min 70% FT faculty (3-5 year), 50% TT (3-5 year) | 1.A (1) Identify number of needed faculty | Ongoing | Associate Dean of Academic Affairs
|  | 1.A.(2) Petition University for appropriate enduring positions | Ongoing | Dean
| 1.B. Retain of part time faculty (Staffing number) for 3-5 year | 1.B.(1) Develop an orientation structure for part time faculty (online) | Review on Yearly Basis | Clinical Coordinator and Level/Program Lead
|  | 1.B.(2) Provide yearly teaching assignments to part time faculty by June | Review on Yearly Basis | Associate Dean of Academic Affairs
|  | 1.B (3) Investigate the feasability of clinical float faculty | Review on Yearly Basis | Clinical Coordinator
| 1.C. Faculty diversity will align with WA state and WA state Schools of nursing demographics | 1.C.(1) Develop recruiting plan to engage and attract a diverse population of faculty (broader outreach - inclusive of under represented faculty) | Review on Yearly Basis | Dean and Search Committee
|  | 1.C.(2) Employ engagement strategies (below) to create culture of diversity and inclusion | Review on Yearly Basis | SoN Representative to the AACN Diversity, Equity, and Inclusion Group
| 1.D. Salaries commensurate with private universities and the geographic region (WEST) | 1.D.(1) Review National/Regional Salary Data as compared to faculty salaries/potential faculty salaries annually | Review on Yearly Basis | Dean
|  | 1.D.(2) Request salary increases as appropriate based upon salary data | Review on Yearly Basis | Dean
| 1.E. Extend program recognition/reputation (Strive for top 50% (remain in top 100 programs) for graduate programs. Improved First time NCLEX Pass Rates (>94%) for all pre-licensure students | 1.E.(1) Increase the Number of Fellows on Faculty | Review Every 2-3 Years | Dean and RAD
|  | 1.E.(2) Increase the number of faculty with certifications in education, simulation, or specialty areas | Review Every 2-3 Years | Dean, CCNL, and RAD
|  | 1.E.(3) Seek and obtain National Grants | Ongoing | Office of Sponsored Programs
|  | 1.E.(4) Seek opportunities and Participate in National Organizations and Committees Nominate faculty to serve | Review on Yearly Basis | SoN Faculty
|  | 1.E.(5) Review and revise a. Admission criteria b. Teaching/Learning/Assessment/Evaluation Strategies c. Student resources and utilization of resources including standardized testing d. Monitor pass rates and areas of content (Mountain Measures) to identify areas to improve and faculty teaching strategies to maximize student learning. (See teaching development below) e.Developing a test development and evaluation committee | See SEP for Specific Dates | PEC, RAP, and CIC
| 1.F. Teaching assignment stability (continuity: at least 2 times) | 1.F.(1). Develop a teaching assignment process | Review on Yearly Basis | Associate Dean of Academic Affairs
|  | 1.F.(2). Implement a plan based on expertise, experience, and evaluative feedback. | Review on Yearly Basis | Associate Dean of Academic Affairs
Engagement: (supports stability) Engagement and motivation/sense of ownership/belonging: “do you feel like you’re part of a team at PLU SoN” 3-5 year goal: Foster a supportive environment that promotes a sense of belonging and provides opportunities for faculty engagement Faculty survey | 2.A. Facilitate formal faculty interaction | 2.A.(1) Implement & sustain a standardized “Common Time” for meetings | Review on Yearly Basis | Associate Dean of Academic Affairs
|  | 2.A.(2) Implement & sustain Faculty Development Seminars (Monthly) | Review on Yearly Basis | RAD
|  | 2.A.(3) Formal team development activities such as Orientation and CE Activities | Review on Yearly Basis | RAD and CCNL
| 2.B. Facilitate informal faculty interaction | 2.B.(1) Promote social activities such as Nurses Week Celebration, Holiday Party, etc. | Ongoing | RAD
|  | 2.B(2). Designate a faculty lounge/shared space to support faculty interaction and social activities (Holiday Party) in all Nursing Buildings | Ongoing | Dean
| 2.C. Determine faculty satisfaction | 2.C.(1) Implement annual faculty satisfaction survey to inform future efforts: Review/Revise/Implement a faculty satisfaction survey process | Review on Yearly Basis | RAD and Dean
| 2.D. Scholarship support | 2.D.(1) Establish a writing club | Review on Yearly Basis | ELM Program Coordinator
|  | 2.D.(2) Establish and monitor a mentor program for faculty (distinguish tenure track vs tenure) | Review on Yearly Basis | RAD
|  | 2.D.(3) Increase grant submissions | Ongoing | Office of Sponsored Programs
|  | 2.D.(4) Hire Student Research Assistants via Independent study, start-up funds, or grant funds | Ongoing | Faculty
Capable: Capable and prepared faculty mix able to integrate depth and breadth of faculty expertise in nursing education and clinical practice necessary to meet SoN mission and goals resulting in high achievement of program outcomes. 3-5 year goal: Evidence of a sustained faculty development and training program addressing faculty teaching learning needs | 3.A. Faculty development and training | 3.A.(1) Teaching development - activities occurring at >twice per semester a. Best practices for teaching, b. Lunch and learn, c. Access to online resources such as NurseTim, archived faculty in-services | Ongoing | RAD
| 3.B. Leadership development | 3.B.(1) Increase faculty involvement in professional organizations (local/state/national) | Ongoing | RAD and Dean
|  | 3.B.(2) Sponsor attendance in order to promote engagement and visibility of PLU in National/ International venues | Ongoing | Dean and RAD
| 3.C. Role & Responsibility | 3.C.(1) Review existing faculty responsibilites as documented in the handbook (ex. course lead, clinical instructor) | Review on Yearly Basis | Leadership Team
|  | 3.C.(2) Increase faculty knowledge of WAC requirements, Accreditation standards, INACSL, AACN Essentials (computer-based learning) | Review on Yearly Basis | Associate Dean of Academic Affairs
| 3.D. Standardized onboarding/orientation process | 3.D.(1) Develop standardized orientation process (full and part time faculty) | 21-22 AY | RAD and Associate Dean of Academic Affairs
|  | 3.D.(2) Implement standardized orientation process (full and part time faculty) | Ongoing | RAD
| 3.E. Have support structure in place | 3.E.(1) Develop process for hiring and implement use of teaching assistants
3.E.(2) Develop process for hiring and implement use of research assistants
|  | 3.E.(3) Evaluate Leadership/reporting structure | Review on Yearly Basis | Leadership Team
|  | 3.E.(4) Evaluate Roles, responsibility, structure of committees | Review on Yearly Basis | SNO and Committees

## Student Support
Student Support PLU will promotes an inclusive environment embracing wellness and resilience, academic/life blend, and sense of community that intentionally supports and promotes diversity and equity.
Goal | Strategy | Action | Dates | Person(s) Responsible
1. Wellness and Resilience Objective: Students will engage in wellness principles as developed and implemented within PLU’s commitment to the centrality of diversity and inclusion throughout their program. | 1.A. Intentionally thread wellness and resilience learning opportunities and resources into each semester of each program to foster resilency in a way that is meaningful, respectful, and inclusive for all students. | 1.A.(1) Conduct gap analysis of current curriculum for existing wellness/resilience content | 2022-05-01 | CIC
|  | 1.A.(2) Based on gap analysis develop plan for a coordinated curriculuar approach that integrates with the overall university plan | 2023-05-01 | CIC
2. Academic/Life Blend Objective: Students in all nursing programs will be informed of and have access to university and professional support resources. | 2.A. Continue to provide students information on accessing student support resources available within the school of nursing and across the university. | 2.A.(1) Include information in student orientation | ongoing | Program Coordinators, Associate Director for Admission & Student Support
|  | 2.A.(2) Include information in Just culture newsletter | Spring 2022 | RAP
| 2.B. Continue to provide information on accessing academic resources (e.g. writing center) | 2.B.(1) Include information in student orientation | ongoing | Program Coordinators, Associate Director for Admission & Student Support
|  | 2.B.(2) Include information in Just culture newsletter | Spring 2022 | RAP
| 2.C. Continue to provide information on accessing professional resources (e.g. NSNA and GSNA) | 2.C.(1) Include information in student orientation | ongoing | Program Coordinators, Associate Director for Admission & Student Support, Delta and GSNA representative
3. Community Objective: Provide opportunities for students to foster diversity and inclusion in the PLU nursing community to cultivate a lifelong identity as a PLU nursing graduate. | 3.A. Create Peer Mentoring Program | 3.A.(1) Identify peer mentor models and methods to assess effectiveness (BSN, MSN) | ongoing | Delta and Delta Faculty Advisors, program coordinators
|  | 3.A.(2) Select, implement and evaluate a peer mentor program | ongoing | Delta and Delta Faculty Advisors, program coordinators
|  | 3.A.(2) Select, implement and evaluate a peer mentor program (DNP) | Fall 2023 | Delta and Delta Faculty Advisors, program coordinators
| 3.B. Provide service learning opportunities as a member of the PLU community | 3.B.(1) Collaborate with University and community to offer and support service activities (e.g. flu clinic, COVID testing, sports physicals) | ongoing | clinical coordinator, CBC coordinator
|  | 3.B.(2) Celebrate and showcase student accomplishments | ongoing | program coordinators, Delta, MARCOM
| 3.C. Create and promote an environment of tolerance, understanding, and acceptance of differing opinions, groups, and communities. | 3.C.(1) Identify educational opportunities for students broaden awareness through exploration and engagement in DEI training. | ongoing | Associate Dean and Program Coordinators (specialized role TBD - see 3.C (4))
|  | 3.C.(2) Provide opportunities to engage in respectful dialogue. (e.g. topics relative to stigmatized and vulnerable groups) | ongoing | All FAculty
|  | 3.C.(3) Explore the need for student and or alumni affiliated groups |  | Leadership Team
|  | 3. C (4) Explore the need for a JEDI liasion |  | Leadership Team

## Program Growth
Program Growth
Goal | Strategy | Action | Dates | Person(s) Responsible
1. Identify opportunities for growth ELMSN & MSN Programs | 1.A. Transition pre-licensure ELM cohorts to separate classes | 1.A (1) Change structure and implement | Fall 2021 | Associate Dean (well done!)
| 1.B. Develop a way for ELMs to work clinically during post-licensure portion of program | 1.B.(1) Develop PT option for post-licensure ELMs | Ongoing- started Fall 2021 | ELM Coordinator
| 1.C. Consider shifting ELM post-licensure to online, part synchronous and asynchronous HYBRID – focus on growing the MSN – focus on education | 1.C.(1) Have faculty discussion regarding possible transition and analyze pros/cons | AY 2021-2022 | ELM Coordinator & Assoc Dean
| 1.D. Create different ELM/MSN tracks | 1.D.(1) Identify tracks to offer (CNL, CNE (possible SIM experience - CHSE), CPH?, Leadership, Informatics?, CNML?) | AY 2021-2022 | ELM Coordinator & Assoc Dean
|  | 1.D.(2) Align with AACN Level 2 Essentials | AY 2021-2022 | ELM Coordinator & Assoc Dean
|  | 1.D.(3) Develop those tracks | AY 2021-2022 | ELM Coordinator & Assoc Dean
| 1.E. Explore pathways to get ELMs to DNP | 1.E.(1) Identify and offer - do gap analysis of coursework | Spring 2022 | ELM, DNP Coordinators & Assoc Dean
|  | 1.E.(2) Integrate clinical requirements for ELM to DNP (do lit search) | Spring 2022 | ELM, DNP Coordinators & Assoc Dean
2. Collaborate with PLU departments to identify opportunities for interprofessional education opportunities and new program development | 2.A. Needs assessment for the local community | 2.A.(1) Review current competitor local and regional programs | Spring 2022 | Dean & Assoc Dean & ELMSN Coordinator
|  | 2.A.(2) Identify unique or absent program offerings to consider | Spring 2022 | Dean & Assoc Dean & ELMSN Coordinator
| 2.B. Connect with other PLU Departments | 2.B.(1) Connect with School of Business (MHA, DNP in Executive Leadership and Healthcare Administation) | Spring 2022 | Dean & Assoc Dean & ELMSN Coordinator
|  | 2.B.(2) Connect with Dept of Social Work (MPH) | Fall 2022 | Dean & Assoc Dean & ELMSN Coordinator
|  | 2.B.(3) Connect with School of Education & Kinesiology (DNP in Educational Leadership) | Fall 2022 | Dean & Assoc Dean & ELMSN Coordinator
| 2.C. Consider additional certifications OR mini-seminars on topics e.g., complementary practices, etc - open to anyone | 2.C.(1) Align needs and resources of PLU Departments to create interprofessional activities (continuing ed, certificate programs, dual degree) | Spring 2023 | Dean & Assoc Dean & ELMSN Coordinator
|  | 2.C (2) review structure of CCNL to ensure sufficient support for CE offerings | Spring 2023 | Dean & Assoc Dean & ELMSN Coordinator
3. Create NP Certificate Programs | 3.A. Needs assessment for the area | 3.A.(1) Conduct a formal needs survey/environmental scan | Ongoing | Assoc Dean and DNP Coordinator
| 3.B. ENP Certificate | 3.B.(1) Conduct a formal needs survey/environmental scan | Completed | Assoc Dean and DNP Coordinator
|  | 3.B.(2) Consult with relevant organization regarding collaboration for certification process | In-progress | Assoc Dean and DNP Coordinator
| 3.C. Explore other certificate programs (e.g, Developmental NP Certificate, Child/Adolescent PMHNP Certificate) | 3.C.(1) Conduct a formal needs survey/environmental scan | Fall 2022 | Assoc Dean and DNP Coordinator
|  | 3.C.(2) Consult with relevant organization regarding collaboration for certification process | Fall 2022 | Assoc Dean and DNP Coordinator
4. BSN & Pre-Licensure Opportunities | 4.A. Broaden selection of clinical opportunities | 4.A.(1) Explore Dedicated Education Units as an option | Spring 2023 | BSN & ELMSN Coordinators, Clinical Coordinator
|  | 4.A.(2) Explore service opportunities for clinical hours. | Fall 2022 | BSN & ELMSN Coordinators, Clinical Coordinator
|  | 4.A.(3) Explore Alternative in-person simulation activities | TBD - dependent on 4.A.4 | BSN & ELMSN Coordinators, Simulation Director
|  | 4.A.(4) Increase staff for simulation center | 2022-01-01 | Dean, Associate Dean, and Simulation Director
|  | 4.A.(5) Coordinate with DNP students Community Based Clinicals | 2022-01-01 | Clinical Coordinator and DNP Coordinators
|  | 4.A.(6) Explore ways to utilize van for community clinicals | 2022-01-01 | Clinical Coordinator and DNP Coordinators
| 4.B. Accelerated Bachelors Program | 4. B (1) Obtain State Approval | Completed | Dean, Associate Dean, and ABSN Coordinator
|  | 4. B (2) Finalize curriculum | Spring, 2022 | Dean, Associate Dean, and ABSN Coordinator
|  | 4.B (3) Hire Faculty | Spring, 2022 | Dean, Associate Dean, and ABSN Coordinator
|  | 4.B (4) Implement program | Fall, 2022 | Dean, Associate Dean, and ABSN Coordinator
5. Offer study Abroad and Immersive Opportunities | 5.A. Develop a Catalog of Study Abroad and Immersive opportunities for students | 5.A.(1)Explore current abroad opportunities for nursing students at PLU | Fall, 2022 | Dean and any interested faculty in coordination with program coordinators
|  | 5.A (2) Review study away/immersive opportunities of our competitors | Fall, 2022 | Dean and any interested faculty in coordination with program coordinators
|  | 5.A (3) Identify potential study away locations | Spring, 2023 | Dean and any interested faculty in coordination with program coordinators
|  | 5.A. (4) Coordinate with Wang Center Develop current and new opportunities | Spring, 2023 | Dean and any interested faculty in coordination with program coordinators
|  | 5.A (5) Create a Master schedule of offerings | Spring, 2023 | Dean and any interested faculty in coordination with program coordinators
6. Expand CCNL Offerings | 6.A. Develop a Catalog of Continuing Education professional development programs | 6.A.(1) Review present continuing education catalog current offerings for nursing, ease of use, accessablility | Spring 2022 | CCNL Director/Program Manager
|  | 6.A. (2) Update courses as needed | Summer 2022 | CCNL Director/Program Manager
|  | 6.A. (3) Resolve accessability and ease of customer use issues (if any) | Summer 2022 | CCNL Director/Program Manager
|  | 6. A. (4) Market revised catalog and location, access | Summer 2022 | CCNL Director/Program Manager
| 6.B. Offer CCNL classes on developing healthcare challenges, such as opiod crisis, health disparities, Covid sequela and trauma-informed teaching | 6.B.(1) Perform knowledge needs assessment | ongoing, Fall 2022 | CCNL Director
|  | 6. B. (2) Determine key topic areas for nursing continuing education | ongoing, Fall 2022 | CCNL Director
|  | 6.B.(3) Develop classes, secure subject matter esperts/instructors | ongoing, Fall 2022 | CCNL Director
| 6.C. Expand asynchronous offerings | 6.C. (1) Streamline registration for asynchronous offeings on CCNL web page | Fall 2022 | CCNL Director/Program Manager
|  | 6.C. (2) Increase number of offerings and expand topics offered | End of year 2022 | CCNL Director/Program Manager
| 6.D. Offer a variety of annual preceptor supportive courses | 6. D. (1) Assess current preceptor offerings | ongoing, Fall 2022 | CCNL Director
|  | 6.D. (2) Perform needs assessment to revise/expand topic areas and modes of course delivery | ongoing, Fall 2022 | CCNL Director
|  | 6.D. (3) Include revised topic areas with spring 2023 calender/catalog | End of year 2022 | CCNL Director
| 6.E. Second nurse planner for CCNL | 6.E. (1) Recruit a second nurse planner | End of year 2022 | CCNL Director
|  | 6.E. (2) Orient a second nurse planner | End of year 2022 | CCNL Director

## Primary Care
Develop an independent, sustainable, and consistent interprofessional healthcare setting to facilitate student practical experience and faculty practice.
Goal | Strategy | Action | Dates | Person(s) Responsible
Provide high quality clinical practice/practicum sites for prelicensure (BSN and ELMSN), MSN/ELMSN, DNP and other PLU students. | 1.A. Identify opportunities for potential partnerships with healthcare facilities | 1.A.(1) Continued conversations with community healthcare facilities. | Spring 2022 | Dean
| 1.B. Garner support from PLU higher administration to establish a practice site | 1.B.(1) Meet with President to discuss options and potential | Spring 2022 | Dean
|  | 1.B.(2) Obtain endorsement from key stakeholders | Spring 2022 | Dean
| 1.C. Establish a practice site | 1.C.(1) Acquire practice site | Spring/Summer 2022 | Dean, University Administration
| 1.D. Define scope of services | 1.D.(1) Establish the SOP's, oversight/operation plan, and administrative structure | Spring/Summer 2022 | Assoc Dean and FNP Coordinator
|  | 1.D.(2) Establish scope of services and implementation plan (integration of telehealth and interprofessional education) | Spring/Summer 2022 | Clinic director and FNP Coordinator
| 1.E. Every student enrolled in the nursing prgram will have at least one rotation within this facility during their educational program | 1.E.(1) Develop student clinical grid | Spring/Summer 2022 | All Program Coordinators, Undergrad and Grad Clinical Placement Coordinators
| 1.F. Utilize site for student scholarly projects. | 1.F.(1) Develop description of potential opportunities within the clinic to share with PLU departments | Fall 2022 | DNP Project Coordinator and Clinical Project Coordinator
Provide a faculty practice site to ensure ongoing competence and meet certification/licensure requirments. | 2.A. Institute new policy and workload release for faculty regarding clinical practice | 2.A.(1) review and revise current policy | Spring/Summer 2022 | Dean, Assoc Dean and FNP Coordinator
| 2.B. Develop faculty work schedules congruent with teaching schedules (clinical grid) | 2.B.(1) Share option for work within clinic with current and prosective faculty | Spring/Summer 2022 | Dean and Assoc Dean
| 2.C. Develop a plan for acquired clinic staff | 2.C.(1) Discussion of conditions of employment (precepting, pay, and benefits) | Spring/Summer 2022 | Dean and Assoc Dean
Provide an array of clinical experiences across the lifespan to ensure interprofessional practice opportunities. | 3.A. Ensure clinical services are offered across the lifespan | 3.A.(1) Define scope of services include lifespan (prenatal, palliative care,geriatrics, family planning, etc) | Summer/Fall 2022 | Clinical director and FNP Coordinator
|  | 3.A. (2) Ensure staffing allows for student training (RN) | Summer/Fall 2022 | Clinic director
| 3.B. Partner with other departments within PLU to ensure interprofessional practice opportunities | 3.B.(1) Partner with department of Social Work, LMFT, Kinesiology | Spring 2023 | Dean, Assoc Dean and Program Coordinators with Clinic Director
|  | 3.B.(2) Consider partnerships with other healthcare related disciplines (including PT, OT, billing and coding, MA, etc) | Spring/Summer 2023 | Dean, Assoc Dean and Program Coordinators with Clinic Director
| 3.C. Incorporate current Community Based Clinicals (CBC) | 3.C.(1) Collect insurance information to bill for Sports Physicals (no cost to patients) | Spring/Summer 2022 | CBC Coordinator and Clinic Director
|  | 3.C.(2) Expand CBCs activities to include primary care services to additional underserved populations (HPSA/MUP), utilize current resources such as the van | Summer/Fall 2022 | CBC Coordinator and Clinic Director
| 3.D. Ensure clinic staff work at the highest level of their training and licensure | 3.D.(1) Ensure protocols in place for pt care | Summer/Fall 2022 | Clinic Director
|  | 3.D.(2) Clearly defined roles and responsibilities for all clinic personnel | Quarterly | Clinic Director
Clinical site will be self-sustainable. | 4.A. Consider partnerships with sustainable facilities only | 4.A. 1) Review financial status of initial partners (profit margins) | Spring 2022 | PLU Admin and Clinic Director
|  | 4.A. 2) Review financial status of future partners for growth | Spring/Summer 2022 and Ongoing | PLU Admin and Clinic Director
| 4.B. Review business plans of potential partners | 4.B.(1) Ensure proper billing processes are in place | Summer 2022 and Ongoing | Clinic Director and Clinic Bookkeeper
|  | 4.B.(2) Educate clinical staff to code and bill accurately (as needed) | Summer 2022 and Ongoing | Clinic Director
| 4.C. Seek funding (grants) for capital improvements and expansion | 4.C.(1) Develop incremental plan for expansion | Summer/Fall 2022 and Ongoing | Dean, Assoc Dean and Program Coordinators with Clinic Director
|  | 4.C.(2) Follow incremental plan for expansion | Spring 2023 and Ongoing | Dean, Assoc Dean and Program Coordinators with Clinic Director
|  | 4.C.(3) Seek Grants for expansion and improvement | Fall 2023 | Dean, Assoc Dean and Program Coordinators with Clinic Director
|  | 4.C.(4) Explore FQHC status and other finanical incentives | Spring 2024 | Clinic Director
| 4.D. Implement NP Residency program | 4.D.(1) Identify FNP Residency Program Models | Summer 2023 | Dean, Assoc Dean and Program Coordinators with Clinic Director
|  | 4. D (2) Seek grants for FNP residency program development | Fall 2022 | Dean, Assoc Dean and Program Coordinators with Clinic Director
|  | 4.D.(3) Establish and recruit for FNP residency | Spring 2023 | Dean, Assoc Dean and Program Coordinators with Clinic Director
|  | 4.D.(4) Utilize graduating residents as preceptors | Fall 2024 | Dean, Assoc Dean and Program Coordinators with Clinic Director